INTERNAL OPERATIONS — NOT PARTICIPANT-FACING Maven Launch SOP Aug–Oct 2026 · v1.2 FINAL

CONFLICT NOTE: no v1.1 (or earlier) version of this SOP was found anywhere in the accessible repository or session. This document is compiled fresh as the current source-of-truth capture for the August–October 2026 launch window, incorporating every frozen Phase 2A, 2B, and 2C decision plus the Phase 2D corrections below — it is not presented as a diff against a predecessor that could not be located. See the Phase 2D QA Report for the same flag.

Phase status

| # | Category | Status | Notes |
| --- | --- | --- | --- |
| 1 | Phase 2A — participant files (Part A, Part B, Complete Session Record) | GREEN | FROZEN. Not edited in Phase 2D. |
| 2 | Phase 2B — solo delivery system | GREEN | FROZEN. Not edited in Phase 2D. |
| 3 | Phase 2C — participant communications | GREEN | FROZEN. Not edited in Phase 2D. |
| 4 | Phase 2D — implementation, rehearsal, launch gates | READY WITH WATCH ITEM | Current phase. Several items require manual verification before launch (see Section D and the Master Prelaunch Gate). |

――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――

Paid workshop — key dates (frozen, Phase 2A–2C)

| Public title | Decide Whether to Stay or Leave Your Job |
| --- | --- |
| Subtitle | A Live Career Growth Assessment |
| Method | The Capability Position Read |
| Brand line | A Capability Formation Workshop |
| Main session | Thursday, September 10, 2026, 6:00–8:00 PM Central Time |
| Price | $500 |
| Capacity | Limited to 12 participants |
| Delivery | Solo facilitator |
| Recording | None for the first paid delivery |
| 30-Day Evidence Review | Thursday, October 8, 2026, 6:00–6:45 PM Central Time |
| 90-day rescore reminder | Wednesday, December 9, 2026 |

These dates are frozen in Phase 2A–2C and repeated here for reference only — this SOP does not alter them.

――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――

A. Participant session record policy

Participants retain their completed Part A and Part B files as their private session record.

Temidayo does not receive participant workbook responses and therefore does not send a pre-filled Complete Session Record after the workshop. Do not promise this delivery in any participant communication, on the Maven page, or verbally during the session.

The Phase 2A Complete Session Record file remains available as an internal / optional structural artifact (a blank consolidation template participants may choose to use on their own), but it is not a promised post-session deliverable and is never described as pre-filled.

――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――

B. Free Lightning Lesson — capacity

| Free Maven registration cap | 200 registrations |
| --- | --- |
| Zoom live participant capacity | 100 participants |

The 200-registration figure is an INTERNAL registration ceiling, not public scarcity language. Do not use "only 200 seats" or similar phrasing anywhere participant-facing — on the Maven page, in emails, on LinkedIn, or on Substack.

If registrations approach a level where expected live attendance could exceed the 100-participant Zoom capacity, review Zoom capacity before continuing promotion — do not wait until the day of the session to discover a shortfall.

――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――

C. Zoom

Free Lightning Lesson

| Account | Zoom Workplace Pro |
| --- | --- |
| Live capacity | 100 participants |
| Session length | 45 minutes — safely within the account's meeting-duration limit |
| Join link | [FREE LIGHTNING LESSON ZOOM LINK] |

Do not publish the private Zoom URL in any participant-facing document. This SOP is internal-only, which is why the join-link row above uses a placeholder rather than the live URL — insert the real link only in the internal operational copy actually used for day-of control, never in anything shared publicly.

Paid Capability Position Read

| Join link | [WORKSHOP JOIN LINK] |
| --- | --- |
| Recording | None for the first paid delivery |
| Late entry | New-entrant cutoff at minute 8; verified-reconnection exception applies (see the Zoom Configuration Checklist) |

――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――

D. Gumroad — Field Kit fulfillment

| Code | CPRSEP26 |
| --- | --- |
| Discount | 100% |
| Product | The Capability Formation Field Kit only |
| Use limit | 15 |
| Current usage | 0 / 15 |
| Start date shown in Gumroad | August 6 at 1:00 PM |
| Workshop capacity (unchanged) | 12 |

The extra three redemptions (15 vs. 12) are operational recovery margin for participant access problems — they do not increase workshop capacity.

Do NOT use CF-READER-25 — that code belongs to Capability Formation paid subscribers and must never be substituted here.

Private auto-discount URL:  [PRIVATE CPRSEP26 AUTO-DISCOUNT LINK — VERIFY]

Redemption deadline:  [FIELD KIT REDEMPTION DEADLINE — VERIFY]

Do not invent an end date or a final redemption deadline. Both require manual verification in the live Gumroad configuration before launch — see the Gumroad Live Fulfillment Checklist.

――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――

E. Launch-readiness checklist — phase status

| # | Category | Status | Notes |
| --- | --- | --- | --- |
| 1 | Phase 2A | GREEN | FROZEN |
| 2 | Phase 2B | GREEN | FROZEN |
| 3 | Phase 2C | GREEN | FROZEN |
| 4 | Phase 2D | READY WITH WATCH ITEM | Current implementation phase — see the Master Prelaunch Gate for the full launch-critical list |

――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――

F. Free Maven page — current copy

| Title | How to Tell If Your Career Is Stalling |
| --- | --- |
| Date | Thursday, August 20, 2026 |
| Time | 6:00–6:45 PM Central (America/Chicago) |
| Duration | 45 minutes |
| Price | Free |

Learning outcomes

1. Separate performance from growth

See why doing excellent work does not automatically mean the role is expanding your judgment, skills, or future range.

2. Test indispensability against portability

Recognize when being indispensable strengthens internal value but not external options.

3. Identify the next question to investigate

Use one example from your last 90 days to identify what deserves a closer reading before a larger career move.

Why this topic matters

“You can be performing well in a role that has quietly stopped building you. Strong reviews, greater responsibility, and being indispensable can all hide a loss of learning or future options. This lesson helps you recognize three patterns before a reorganization, an external opportunity, or a change in your role makes the question urgent.”

Instructor short line

“Org capability strategist. Author, The Capability Audit. PwC, Deloitte, EY.”

Character count: 75 / 80 (Maven limit).

Do not add employer logos to Brand Associations.

――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――

CAPABILITY FORMATION — MAVEN LAUNCH SOP  ·  Aug–Oct 2026  ·  v1.2 FINAL  ·  INTERNAL ONLY