INTERNAL OPERATIONS Master Prelaunch Gate Free Lightning Lesson + Paid Capability Position Read

Four statuses: GREEN, READY WITH WATCH ITEM, BLOCKED, NOT APPLICABLE. The overall launch may not be labeled GREEN until every launch-critical item is GREEN or READY WITH WATCH ITEM, with zero unresolved BLOCKED items.

| # | Category | Status | Notes |
| --- | --- | --- | --- |
| 1 | Offer | GREEN | Title, price, capacity, dates, and method are locked and consistent across every frozen phase. |
| 2 | Free Maven page | READY WITH WATCH ITEM | Copy specified in the Launch SOP Section F; page is still being built/published — verify the live page matches exactly once published. |
| 3 | Paid Maven page | READY WITH WATCH ITEM | Content fully specified (title, price $500, cap 12, Sept 10); live-page and checkout verification pending — see Implementation Checklist Section B. |
| 4 | Zoom | READY WITH WATCH ITEM | Both accounts and capacities identified; the Zoom Configuration and Testing checklist is created but not yet executed. |
| 5 | Free deck | READY WITH WATCH ITEM | v3.2 FINAL ("How to Tell If Your Career Is Stalling") treated as current per the Phase 2D title. A second, older deck family ("Is Your Work Still Building You?", v1.0) also exists in the repo under a different title — Temidayo must confirm which is live on Maven and retire the other. See Master Asset Index notes. |
| 6 | Paid deck | GREEN | v5.2.1 FINAL — single unambiguous source, checksum-verified unchanged throughout Phases 2B and 2C. |
| 7 | Participant files | GREEN | Phase 2A — FROZEN, unchanged. |
| 8 | Solo delivery system | GREEN | Phase 2B — FROZEN, unchanged. |
| 9 | Participant communications | GREEN | Phase 2C — FROZEN, unchanged. |
| 10 | Gumroad | BLOCKED | Code/discount/product/use-limit are locked (CPRSEP26, 100%, Field Kit only, 15 uses), but the private auto-discount URL is not yet created/tested, no $0 checkout test has been run, and the redemption deadline has not been chosen. None of these may be invented — see the Gumroad Live Fulfillment Checklist. |
| 11 | Website | READY WITH WATCH ITEM | No verification data available in this phase — requires separate manual confirmation that any website copy referencing either offer is current. |
| 12 | LinkedIn | READY WITH WATCH ITEM | No verification data available in this phase — confirm CPRSEP26 never appears publicly here before any promotional post goes out. |
| 13 | Substack | READY WITH WATCH ITEM | Serves as the free session's secondary conversion route — confirm the link is live and correct before Aug 20. |
| 14 | Free rehearsal 1 | BLOCKED | Not yet run — protocol authored this phase. |
| 15 | Free rehearsal 2 | BLOCKED | Not yet run — protocol authored this phase. |
| 16 | Paid rehearsal 1 | BLOCKED | Not yet run — protocol authored this phase. |
| 17 | Paid rehearsal 2 | BLOCKED | Not yet run — protocol authored this phase. |
| 18 | Conversion links | BLOCKED | Section D pre-launch tests (paid link, price, capacity, date, checkout, welcome email) not yet executed. |
| 19 | 30-Day Evidence Review | READY WITH WATCH ITEM | Content frozen (Phase 2C v1.2); live Zoom link for Oct 8 still pending. |
| 20 | 90-day follow-through | READY WITH WATCH ITEM | Content and policy frozen (Phase 2C v1.1); send-mechanics for the Dec 9 reminder not yet tested. |

――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――

Overall result

NOT YET GREEN — 6 unresolved BLOCKED items remain (Gumroad configuration, all four required rehearsals, and the conversion-link pre-launch tests).

This is the expected state at this point in Phase 2D — the blockers are scheduled, testable actions (run the rehearsals, complete the Gumroad verification, run the conversion tests), not open design questions. Re-run this gate after each blocked category clears.

――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――

CAPABILITY FORMATION — MASTER PRELAUNCH GATE v1.0  ·  INTERNAL ONLY