INTERNAL OPERATIONS Paid Workshop — Full Rehearsal Protocol Decide Whether to Stay or Leave Your Job

Two complete rehearsals are required before September 10. Neither may be skipped or combined.

――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――

Rehearsal 1 — Method and timing

Purpose: confirm the full 105-minute guided core runs at its correct pace and sequence, solo, spoken aloud in full.

Focus

Exact 105-minute guided core, start to finish

Part A

Poll A1 (readiness)

Poll A2 (initial placement)

Staged Part B release — full response-count verification procedure

Evidence protocol

Second read

Sensitivity procedure

Poll B

Poll C

State-cost section

Move categories

8-minute protected writing block

Voluntary reads

Close

Q&A at minute 105 (hard start)

――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――

Rehearsal 2 — Full solo production simulation

Purpose: confirm Temidayo can operate every technical layer alone, without an assistant, while also teaching.

Temidayo must operate, unassisted

Deck

Zoom

Waiting room

Polling

Chat

Part B release

Timer

Notes

Transitions

――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――

Rehearsal 2 — simulated scenarios

Run at least all eleven scenarios below during Rehearsal 2. For each, document the approved response, the recovery action, what must not happen, and whether timing recovers before minute 105.

1.  Participant asks a question during scoring

APPROVED RESPONSE:  Acknowledge briefly, redirect to the Q&A boundary line, do not answer live during a protected scoring window.

RECOVERY ACTION:  Continue the scoring window without interruption; hold the question for Q&A.

WHAT MUST NOT HAPPEN:  Do not stop the room's scoring rhythm to answer in the moment.

Timing recovers before minute 105: Yes — no time lost if the redirect is immediate and scripted.

2.  One poll response is missing

APPROVED RESPONSE:  Verify the response count against active participants before advancing; if short, use the scripted "one or more responses are still outstanding" line.

RECOVERY ACTION:  Wait, do not release Part B or move to the next poll until the count matches.

WHAT MUST NOT HAPPEN:  Do not release Part B or advance based on a visual scan or assumption.

Timing recovers before minute 105: Yes — the built-in one-minute allowance absorbs this without falling behind.

3.  Someone needs another minute

APPROVED RESPONSE:  Grant one additional minute to the whole room and repeat the readiness check.

RECOVERY ACTION:  Re-poll Screen A1 after the extra minute; do not single out the individual.

WHAT MUST NOT HAPPEN:  Do not proceed with a partial-readiness room.

Timing recovers before minute 105: Yes — this is the built-in allowance, not an overrun.

4.  Someone disconnects after minute 8

APPROVED RESPONSE:  This is a verified reconnection, not a new entrant.

RECOVERY ACTION:  Readmit at the next natural pause via waiting-room control.

WHAT MUST NOT HAPPEN:  Do not treat this the same as a new-entrant admission request; do not use a hard meeting lock that would block their return.

Timing recovers before minute 105: Yes — readmission at a natural pause costs no scoring time.

5.  One participant joins after minute 8

APPROVED RESPONSE:  This is a new entrant and is not admitted — the assessment method has already begun.

RECOVERY ACTION:  Leave them in the waiting room; direct any follow-up to support after the session.

WHAT MUST NOT HAPPEN:  Do not admit a new entrant after minute 8 under any circumstance, including a sympathetic case.

Timing recovers before minute 105: Yes — no admission action is taken, so no time is spent.

6.  A singleton state appears

APPROVED RESPONSE:  Never display or read aloud a count of one; do not let a singleton drive deeper state-cost teaching.

RECOVERY ACTION:  If no state has 2+, teach all four states evenly without disclosing why.

WHAT MUST NOT HAPPEN:  Do not name, imply, or hint at a singleton count at any point.

Timing recovers before minute 105: Yes — this is a teaching-content decision made once, not a live delay.

7.  Part B link fails once

APPROVED RESPONSE:  Use the pre-tested backup anonymous poll; if that also fails, skip the metric and mark it unavailable on the capture sheet.

RECOVERY ACTION:  Retry once with the backup, then move on without the metric — do not improvise an identifiable substitute.

WHAT MUST NOT HAPPEN:  Do not fall back to show of hands, named chat, direct message, or verbal disclosure.

Timing recovers before minute 105: Yes, if the backup succeeds quickly; if skipped, the room loses no time waiting.

8.  Participant cannot open the PDF

APPROVED RESPONSE:  Point them to the print/manual-total fallback; the method does not depend on the form fields working.

RECOVERY ACTION:  They continue in the room using paper or a blank document; direct off-session troubleshooting to support.

WHAT MUST NOT HAPPEN:  Do not stop the room to troubleshoot one participant's PDF live.

Timing recovers before minute 105: Yes — the fallback keeps them moving with the room.

9.  Session runs two minutes behind

APPROVED RESPONSE:  Apply the named cut order before minute 105: voluntary reads, extended state-cost discussion, extra calibration examples, appendix discussion.

RECOVERY ACTION:  Recover the two minutes from the cut-order list, in order, starting with voluntary reads.

WHAT MUST NOT HAPPEN:  Do not cut into the protected 8-minute writing block, the evidence protocol, or the sensitivity procedure to recover time.

Timing recovers before minute 105: Yes — recovery happens before minute 105 by design; Q&A itself is never shortened for this.

10.  Participant asks "Should I quit?"

APPROVED RESPONSE:  Use the Q&A boundary line: "I can help you clarify what your evidence supports. I cannot make the employment decision for you."

RECOVERY ACTION:  Redirect to their own evidence and placement; do not answer the question as asked.

WHAT MUST NOT HAPPEN:  Do not give a direct yes/no employment recommendation under any framing.

Timing recovers before minute 105: Yes — this is a scripted redirect, not an open-ended discussion.

11.  Someone volunteers too much identifying information

APPROVED RESPONSE:  Redirect using the permission-script boundary; do not repeat identifying details back to the room.

RECOVERY ACTION:  Thank them briefly, steer back to the evidence-based language the method uses.

WHAT MUST NOT HAPPEN:  Do not name their employer, ask follow-up questions that invite more identifying detail, or repeat what they shared verbatim.

Timing recovers before minute 105: Yes — a brief redirect costs seconds, not minutes.

――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――――

CAPABILITY FORMATION — PAID WORKSHOP FULL REHEARSAL PROTOCOL v1.0  ·  INTERNAL ONLY